## Plan
IVPM2 Level 1 & 2 Project Plan — Autonomous Warehouse Inspection Drone (AWID)
Project window: May 2026 – Apr 2027 ¦ Level 1 = Fix Version s + Epics ¦ Level 2 = Task deliverables (≤ 2 weeks) ¦ Use the outline buttons at the top-left of the sheet (1 / 2 / 3) to collapse & expand.
[12 empty] | Phase 1 - Detailed Design, Gate: CDR (Critical Design Review) | [7 empty] | Phase 2 - Prototype Development, Gate: PAR (Prototype Acceptance Review) | [11 empty] | Phase 3 - Final Development, Gate: PRR (Production Readiness Review) | [7 empty] | Phase 4 - System Integration, Gate: SIR (System Integration Review) |  |  |  | Phase 5 - Verification, Gate: VRR (Verification Readiness Review) | [7 empty] | Phase 6 - Validation & Acceptance, Gate: VAR (Validation & Acceptance Review) |  |  |  | Phase 7 - Handover & Closure, Gate: Project Closure
[12 empty] | 2026-05-01 |  |  |  | 2026-06-01 |  |  |  | 2026-07-01 |  |  |  | 2026-08-01 |  |  |  | 2026-09-01 |  |  |  | 2026-10-01 |  |  |  | 2026-11-01 |  |  |  | 2026-12-01 |  |  |  | 2027-01-01 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  | 2027-04-01
ID | Type | Name | Fix Version | Start Wk | End Wk | Dur (wks) | Story Pts | Dependencies | Assignees | Status | Notes | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
1 | Component | Systems Engineering & Management | P1-P7 | 1 | 48 | 48 | 57 |  |  | Plan
1.1 | Epic | System-level detailed design | P1 | 1 | 8 | 8 | 16 |  |  | Plan
1.1.1 | Task | Finalise system architecture document | P1 | 1 | 2 | 2 | 3 |  |  | Plan
1.1.2 | Task | Update system requirements baseline | P1 | 2 | 3 | 2 | 2 |  |  | Plan
1.1.3 | Task | Draft & review Interface Control Docs | P1 | 3 | 6 | 4 | 8 |  |  | Plan
1.1.4 | Task | Risk register refresh & mitigation plan | P1 | 7 | 8 | 2 | 3 |  |  | Plan
1.2 | Epic | Integration & V&V master planning | P1-P2 | 5 | 12 | 8 | 18 |  |  | Plan
1.2.1 | Task | Integration plan v1 | P1 | 5 | 7 | 3 | 5 |  |  | Plan
1.2.2 | Task | V&V master plan | P1-P2 | 7 | 10 | 4 | 8 |  |  | Plan
1.2.3 | Task | Test procedures outline | P2 | 10 | 12 | 3 | 5 |  |  | Plan
1.3 | Epic | Gate reviews & project coordination | P1-P7 | 1 | 48 | 48 | 23 |  |  | Plan
1.3.1 | Task | CDR preparation & dry-run | P1 | 7 | 8 | 2 | 5 |  |  | Plan
1.3.2 | Task | PAR preparation & dry-run | P2 | 19 | 20 | 2 | 5 |  |  | Plan
1.3.3 | Task | PRR preparation & dry-run | P3 | 27 | 28 | 2 | 5 |  |  | Plan
1.3.4 | Task | SIR / VRR / VAR coordination | P4-P6 | 31 | 44 | 14 | 8 |  |  | Plan
2 | Component | Airframe & Mechanical Structure | P1-P4 | 1 | 31 | 31 | 50 |  |  | Plan
2.1 | Epic | Detailed mechanical design | P1 | 1 | 7 | 7 | 13 |  |  | Plan
2.1.1 | Task | Frame CAD finalisation | P1 | 1 | 3 | 3 | 5 |  |  | Plan
2.1.2 | Task | FEA / stress analysis | P1 | 3 | 5 | 3 | 5 |  |  | Plan
2.1.3 | Task | DFM review & rework | P1 | 5 | 7 | 3 | 3 |  |  | Plan
2.2 | Epic | Prototype airframe fabrication | P2 | 9 | 16 | 8 | 16 |  |  | Plan
2.2.1 | Task | Raw-material & COTS procurement | P2 | 9 | 10 | 2 | 3 |  |  | Plan
2.2.2 | Task | Machining & additive manufacturing | P2 | 10 | 14 | 5 | 8 |  |  | Plan
2.2.3 | Task | Prototype assembly | P2 | 14 | 16 | 3 | 5 |  |  | Plan
2.3 | Epic | Production airframe build | P3 | 21 | 28 | 8 | 16 |  |  | Plan
2.3.1 | Task | Tooling & fixtures setup | P3 | 21 | 24 | 4 | 8 |  |  | Plan
2.3.2 | Task | First-batch fabrication | P3 | 24 | 28 | 5 | 8 |  |  | Plan
2.4 | Epic | Mechanical integration | P4 | 29 | 31 | 3 | 5 |  |  | Plan
2.4.1 | Task | Mounting & fit-check on prod airframe | P4 | 29 | 31 | 3 | 5 |  |  | Plan
3 | Component | Propulsion System | P1-P2 | 1 | 16 | 16 | 19 |  |  | Plan
3.1 | Epic | Motor/ESC selection & procurement | P1 | 1 | 6 | 6 | 8 |  |  | Plan
3.1.1 | Task | Thrust & efficiency analysis | P1 | 1 | 2 | 2 | 3 |  |  | Plan
3.1.2 | Task | Vendor evaluation & selection | P1 | 2 | 4 | 3 | 3 |  |  | Plan
3.1.3 | Task | Procurement | P1 | 4 | 6 | 3 | 2 |  |  | Plan
3.2 | Epic | Propulsion integration & characterisation | P2 | 9 | 16 | 8 | 11 |  |  | Plan
3.2.1 | Task | Motor-ESC bench test | P2 | 9 | 11 | 3 | 5 |  |  | Plan
3.2.2 | Task | Integration with airframe | P2 | 14 | 16 | 3 | 3 |  |  | Plan
3.2.3 | Task | Vibration characterisation | P2 | 15 | 16 | 2 | 3 |  |  | Plan
4 | Component | Power & Energy Management | P1-P5 | 1 | 36 | 36 | 27 |  |  | Plan
4.1 | Epic | Battery pack & PDB design | P1 | 1 | 6 | 6 | 11 |  |  | Plan
4.1.1 | Task | Battery pack specification | P1 | 1 | 2 | 2 | 3 |  |  | Plan
4.1.2 | Task | PDB schematic & layout | P1 | 3 | 6 | 4 | 8 |  |  | Plan
4.2 | Epic | Power system build | P2 | 9 | 14 | 6 | 10 |  |  | Plan
4.2.1 | Task | BMS integration | P2 | 9 | 11 | 3 | 5 |  |  | Plan
4.2.2 | Task | Harness fabrication | P2 | 12 | 14 | 3 | 5 |  |  | Plan
4.3 | Epic | Power system V&V | P5 | 33 | 36 | 4 | 6 |  |  | Plan
4.3.1 | Task | Endurance / runtime testing | P5 | 33 | 34 | 2 | 3 |  |  | Plan
4.3.2 | Task | Thermal characterisation | P5 | 35 | 36 | 2 | 3 |  |  | Plan
5 | Component | Flight Control Electronics | P1-P5 | 1 | 38 | 38 | 34 |  |  | Plan
5.1 | Epic | FC board & firmware finalisation | P1 | 1 | 5 | 5 | 8 |  |  | Plan
5.1.1 | Task | Autopilot board selection | P1 | 1 | 2 | 2 | 3 |  |  | Plan
5.1.2 | Task | Firmware baseline & PID tuning prep | P1 | 3 | 5 | 3 | 5 |  |  | Plan
5.2 | Epic | FC integration & bench test | P2 | 10 | 16 | 7 | 13 |  |  | Plan
5.2.1 | Task | Hardware-in-the-loop (HIL) simulation | P2 | 10 | 12 | 3 | 8 |  |  | Plan
5.2.2 | Task | Bench-level FC tests | P2 | 13 | 16 | 4 | 5 |  |  | Plan
5.3 | Epic | Flight-mode tuning | P5 | 33 | 38 | 6 | 13 |  |  | Plan
5.3.1 | Task | Tethered flight tuning | P5 | 33 | 35 | 3 | 5 |  |  | Plan
5.3.2 | Task | Free flight tuning | P5 | 36 | 38 | 3 | 8 |  |  | Plan
6 | Component | Navigation & Sensors | P1-P5 | 1 | 40 | 40 | 37 |  |  | Plan
6.1 | Epic | Sensor suite detailed design | P1 | 1 | 7 | 7 | 11 |  |  | Plan
6.1.1 | Task | LiDAR selection | P1 | 1 | 2 | 2 | 3 |  |  | Plan
6.1.2 | Task | IMU / GPS selection | P1 | 2 | 4 | 3 | 3 |  |  | Plan
6.1.3 | Task | Sensor fusion architecture | P1 | 5 | 7 | 3 | 5 |  |  | Plan
6.2 | Epic | Sensor integration & calibration | P2 | 11 | 18 | 8 | 13 |  |  | Plan
6.2.1 | Task | Sensor mounting & alignment | P2 | 11 | 13 | 3 | 5 |  |  | Plan
6.2.2 | Task | Calibration routines | P2 | 14 | 18 | 5 | 8 |  |  | Plan
6.3 | Epic | Navigation V&V | P5 | 35 | 40 | 6 | 13 |  |  | Plan
6.3.1 | Task | Positioning accuracy tests | P5 | 35 | 37 | 3 | 5 |  |  | Plan
6.3.2 | Task | GPS-denied navigation tests | P5 | 38 | 40 | 3 | 8 |  |  | Plan
7 | Component | Communications | P1-P4 | 3 | 32 | 30 | 16 |  |  | Plan
7.1 | Epic | Telemetry & data-link design | P1 | 3 | 7 | 5 | 8 |  |  | Plan
7.1.1 | Task | Radio selection | P1 | 3 | 4 | 2 | 3 |  |  | Plan
7.1.2 | Task | Link-budget analysis | P1 | 5 | 7 | 3 | 5 |  |  | Plan
7.2 | Epic | Comms integration & range test | P4 | 29 | 32 | 4 | 8 |  |  | Plan
7.2.1 | Task | Integration on production airframe | P4 | 29 | 30 | 2 | 3 |  |  | Plan
7.2.2 | Task | Range & resilience testing | P4 | 31 | 32 | 2 | 5 |  |  | Plan
8 | Component | Inspection Payload | P1-P5 | 5 | 40 | 36 | 21 |  |  | Plan
8.1 | Epic | Inspection-payload integration | P1-P2 | 5 | 18 | 14 | 11 |  |  | Plan
8.1.1 | Task | Camera & gimbal selection | P1 | 5 | 6 | 2 | 3 |  |  | Plan
8.1.2 | Task | Mechanical mounting | P2 | 15 | 16 | 2 | 3 |  |  | Plan
8.1.3 | Task | On-board data pipeline | P2 | 16 | 18 | 3 | 5 |  |  | Plan
8.2 | Epic | Payload V&V | P5 | 37 | 40 | 4 | 10 |  |  | Plan
8.2.1 | Task | Image-quality tests | P5 | 37 | 38 | 2 | 5 |  |  | Plan
8.2.2 | Task | End-to-end inspection workflow test | P5 | 39 | 40 | 2 | 5 |  |  | Plan
9 | Component | On-board Software & Autonomy | P1-P6 | 5 | 42 | 38 | 65 |  |  | Plan
9.1 | Epic | Autonomy software finalisation | P1-P2 | 5 | 20 | 16 | 34 |  |  | Plan
9.1.1 | Task | Mission planner module | P1-P2 | 5 | 10 | 6 | 13 |  |  | Plan
9.1.2 | Task | Obstacle avoidance module | P2 | 9 | 16 | 8 | 13 |  |  | Plan
9.1.3 | Task | Flight state machine | P2 | 15 | 20 | 6 | 8 |  |  | Plan
9.2 | Epic | Software integration on hardware | P4 | 29 | 32 | 4 | 10 |  |  | Plan
9.2.1 | Task | HW-SW integration | P4 | 29 | 30 | 2 | 5 |  |  | Plan
9.2.2 | Task | SIL / HIL regression | P4 | 31 | 32 | 2 | 5 |  |  | Plan
9.3 | Epic | Software V&V | P5-P6 | 33 | 42 | 10 | 21 |  |  | Plan
9.3.1 | Task | Unit & integration test campaign | P5 | 33 | 36 | 4 | 8 |  |  | Plan
9.3.2 | Task | Field flight-test campaign | P5-P6 | 37 | 42 | 6 | 13 |  |  | Plan
10 | Component | Ground Station & Operations | P2-P7 | 13 | 48 | 36 | 63 |  |  | Plan
10.1 | Epic | GCS software development | P2-P3 | 13 | 24 | 12 | 26 |  |  | Plan
10.1.1 | Task | UI development | P2 | 13 | 18 | 6 | 13 |  |  | Plan
10.1.2 | Task | Mission upload / telemetry display | P2-P3 | 19 | 24 | 6 | 13 |  |  | Plan
10.2 | Epic | Field deployment kit | P3 | 21 | 26 | 6 | 11 |  |  | Plan
10.2.1 | Task | Kit hardware procurement | P3 | 21 | 22 | 2 | 3 |  |  | Plan
10.2.2 | Task | Ruggedisation & packaging | P3 | 23 | 26 | 4 | 8 |  |  | Plan
10.3 | Epic | Validation & handover | P6-P7 | 41 | 48 | 8 | 26 |  |  | Plan
10.3.1 | Task | Customer acceptance test | P6 | 41 | 44 | 4 | 13 |  |  | Plan
10.3.2 | Task | Training & operational handover | P7 | 45 | 48 | 4 | 13 |  |  | Plan
Note on H8: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H13: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H17: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H23: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H27: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H31: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H34: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H37: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H41: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H46: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H49: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H52: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H56: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H59: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H62: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H66: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H70: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H73: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H77: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H80: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H84: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H88: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H92: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H96: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H99: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H103: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H106: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.
Note on H109: Story-point scale (Fibonacci, relative effort): 1 = trivial, a few hours 2 = ~ half a day 3 = ~ 1 day 5 = 2–3 days 8 = ~ 1 week 13 = ~ 2 weeks (MAX for a mid-level deliverable) 21 = too large – split it. Assign only at the mid-level row. Macro and component rows sum their children via the =SUM(...) formula.

## Instructions & Legend
How to read & use this plan
1. Collapsing & expanding the plan
In the 'Plan' sheet, look at the top-left corner: you will see three small buttons labelled 1, 2, 3.
• Click '1' to collapse everything down to Component rows only.
• Click '2' to show Components + Epics (full IVPM2 Level 1 view).
• Click '3' to show Components + Epics + Task deliverables (full Level 1 + Level 2 view).
You can also click the small '+' and '-' symbols in the left margin to expand or collapse a single component or epic individually.
2. Row types
COMPONENT — a big area of work; usually a subsystem of the end product. Dark charcoal bar. Rolls up its children.
Epic (IVPM2 Level 1) — a major work item within a component, can span weeks to months. Coloured by Fix Version .
Task DELIVERABLE (IVPM2 Level 2) — a breakdown of a macro; each one must fit in ≤ 2 weeks. Light bar, coloured by Fix Version .
3. Fix Version s (stage-gates) and their gate reviews
P1 | Fix Version 1 - Detailed Design | Week 1 – 8 | Gate: CDR (Critical Design Review)
P2 | Fix Version 2 - Prototype Development | Week 9 – 20 | Gate: PAR (Prototype Acceptance Review)
P3 | Fix Version 3 - Final Development | Week 21 – 28 | Gate: PRR (Production Readiness Review)
P4 | Fix Version 4 - System Integration | Week 29 – 32 | Gate: SIR (System Integration Review)
P5 | Fix Version 5 - Verification | Week 33 – 40 | Gate: VRR (Verification Readiness Review)
P6 | Fix Version 6 - Validation & Acceptance | Week 41 – 44 | Gate: VAR (Validation & Acceptance Review)
P7 | Fix Version 7 - Handover & Closure | Week 45 – 48 | Gate: Project Closure
4. Story-point scale (use Fibonacci; assign at Task)
1 | Minimum effort, A few hours, No complexity, No uncertainty
2 | Slight effort, Half a day, Low complexity, No uncertainty
3 | Mild effort, A day, Slight complexity, Low uncertainty
5 | Moderate effort, 2-3 days, Medium complexity, Moderate uncertainty
8 | Considerable effort, 1 week, Moderate complexity, Moderate uncertainty
13 | Significant effort, 2 weeks, High complexity, High uncertainty
Component and Epic rows do NOT take a manually-entered story-point value — the template auto-sums them from their Task children using =SUM(...). If you add new Task rows, extend the SUM range.
5. Optional columns (IVPM2 does not require these at Level 1 / 2)
Dependencies: write the ID of the predecessor task(s), e.g. '3.1.3, 4.1.1'.
6. How to extend the template
• Add a new component: insert rows at the bottom, give outline level 0 to the component row, level 1 to its epics level 2 to its Tasks.
• Add a new Task under an existing epic: insert a row inside the epic's block, set its outline level to 2, and update the epic's =SUM(...) range.
• Re-schedule: change Start Wk / End Wk. The Dur column auto-updates; you will need to repaint the timeline bar manually (or just re-run the generator).
7. Assignee
• Assignee need to correspond to those available in jira on a particular site